## Planning
NOTE: Only change the date below
First day of the conference | 2026-03-23
Name Conference
Activitity | weeks before the conference | deadline
Start project | 52 | 2025-03-24
Strategy & structure are defined | 51 | 2025-03-31
Date and venue have been secured | 50 | 2025-04-07
Organising Committee is assembled | 50 | 2025-04-07
Preliminary budget is drafted | 50 | 2025-04-07
Concept & Commitments are ready | 50 | 2025-04-07
Program structure has been finalized | 49 | 2025-04-14
Conference information is ready to be distributed (for sponsoring) | 49 | 2025-04-14
Spreakers form is ready | 49 | 2025-04-14
Marketing plan is ready | 45 | 2025-05-12
Website can be launched | 40 | 2025-06-16
Website is filled with: at least chair, themes, 3 keynotes | 36 | 2025-07-14
Save the date can be sent | 34 | 2025-07-28
50% of the programme is ready | 16 | 2025-12-01
70% of the programme is ready | 12 | 2025-12-29
Evaluation is ready | 8 | 2026-01-26
90% of the programme is ready | 8 | 2026-01-26
Setup & Team Briefing | 1 | 2026-03-16
Conference day | 0 | 2026-03-23
Follow-up & Evaluate
Formulas:
deadline = B2 - [weeks before the conference] * 7

## Strategy & Structure
Strategy & Structure
Define your objectives
Why are you organising this event?
What do you want to achieve (knowledge exchange, visibility, partnerships, leads)?
Define key metrics: target audience, desired number of attendees, international reach, etc.
Choose your theme or focus
Align with regional or sector strengths.
Ensure the topic is future-oriented and relevant to your ecosystem.
Assemble your core team
Assign key roles:
Programme lead
Marketing & communications
Operations coordinator
Finance & partnerships
Define responsibilities and expectations early on.
Shortlist dates and potential venues
Consider international calendars, holidays, and competitor events.
Conduct a short survey among your target audience if needed.
Start initial conversations with preferred venues.
Draft your preliminary budget
Estimate costs and income streams: registration fees, sponsorships, exhibition space, public funding.
Identify potential funding partners and ecosystem contributors.

## Concept & Commitments
Concept & Commitments
Secure your main attractions and keynotes
Choose a speaker or element that adds international appeal and credibility.
Confirm availability and budget early.
Approach sponsors and partners
Share your vision, objectives, and key attractions.
Offer clear sponsor packages with visibility and impact options.
Draft your event concept plan
Include programme structure, audience journey, partner involvement, side events, and social programme.
Develop your brand identity
Create a visual identity and tone-of-voice in line with the event theme.
This branding will be used for your website, socials, signage, and delegate materials.

## Launch & Logistics
Launch & Logistics
Launch your event website and registration
Provide practical info and clear registration flow.
Include logistical questions (dietary needs, accessibility, T-shirt size, arrival time, etc.).
Start promotion
Announce early bird tickets and keynote(s).
Use LinkedIn, email marketing, media outreach, and partner networks.
Prepare press materials and media contacts list.
Confirm key programme elements
Finalise speakers, panels, workshops, entertainment, moderators.
Publish a preliminary programme if possible.
Coordinate logistics
Catering, AV, safety, signage, accessibility.
Confirm contracts and responsibilities with suppliers and vendors.

## Setup & Team Briefing
Setup & Team Briefing
Set up venue
Registration desks, stages, signage, tech test.
Ensure all materials (digital and physical) are on-site.
Brief your volunteers
Provide them with a clear schedule and assign them to a team lead.
Distribute team contact sheet and on-site communication method (e.g. WhatsApp group).
Confirm media attendance
Double check who is coming and where interviews will take place.

## Follow-up & Evaluate
Follow-up & Evaluate
Send thank-you messages
Tailor them for: attendees, volunteers, speakers, and partners.
Mention results: attendance, media coverage, standout moments.
Send post-event survey
Assess the event’s success, gather ideas for improvement, and measure your impact.
Share a summary of outcomes with your stakeholders.